## Sheet1
Effectiveness of de-hazing methods on USOD models
					Effectiveness of de-hazing methods on USOD models
Task	Start Date	Days needed	Completion	Adjusted Length
Finalise scope	15/02/2026	8	46076.00	8
Literature Review	19/02/2026	10	46082.00	10
Data Pipeline Setup	01/03/2026	9	46091.00	9
Baseline Model Setup	07/03/2026	11	46099.00	11
Model Refinement	18/03/2026	13	46112.00	13
Testing	22/03/2026	15	46118.00	15
Analysis	29/03/2026	9	46119.00	9
Final Report Write up	03/04/2026	22	46137.00	22
Figure Production	06/04/2026	6	46124.00	6
Final Corrections	25/04/2026	7	46144.00	7

		46068.00
		46150.00